## Sheet1
Use case |  |  | Miles stones to be recorded | Priority
BlockChain | We are creating a way for people to interact with HCM and various important milestones to be recorded | 1 | Creating a user
|  | 2 | Uploading Personal info | *
|  | 3 | Conferation of security check | *
|  | 4 | Payroll enrollment | *I
|  | 5 | Enrollment of Benefits
|  | 6 | File for visa

## Task List
Completed tasks
| Taleo ENV | Up
| HCM Env | up
| Block Chain Env | up | Check login in tab for login info
Task To be completed
Sl No | Task | Who is Working | Comment | Status
1 | Chat Bot development With HCM Integration | Amit/Aditya | Amit-Chatbot Development done with HCM integration.Only Update part is pending
2 | Mobile Backend development for HCM Integration | Amit/Aditya | Amit-Mobilebackend code is done
3 | Block Chain smart contract to pull HCM Update from bot to block chain | Ravi |  | Ilya - 2.15 - Working on cleaning up code and added milestone parameters, haven't debugged it yet
4 | Chat Bot development With taleo Integration | Amit/Aditya | Amit-Imported the assets from Demo.Oracle. Need to find out how to connect with our GSE Taleo instance
5 | Mobile Backend development for Taleo Integration | Amit/Aditya | Amit-Imported the assets from Demo.Oracle. Need to find out how to connect with our GSE Taleo instance
6 | Block Chain smart contract to pull Taleo Update from bot to block chain
7 | HCM Atom integration with OIC to Block chain
8 | Chain code - Taleo side |  | 2.14 - Ilya - working on HCM stuff first, since we don’t know if Apis will work
9 | Chain code - HCM side | Ilya
10 | Node js server to ping HCM server | Darshan
11 | Figure out a way to modify hcm to show changes / api connection | Ilya |  | 2.14 | Pending
12 | Transaction Visualizer for blockchain | TBD
13 | Connect Taleo to OIC to Blockchain through api | Darshan | 2.14 - darshan - working with alex about getting more info
Notes
Ilya | Added Milestones to Blockchain structure
2.15 | Added milestones screen shot from actual work flow from client

## Login Information
Block Chain Tenancy
Account | orasenatdhubsblue02
Username | SSO
Password | SSO
Rest proxy | https://08907A5277DF46A9B24950C4023F710A.blockchain.ocp.oraclecloud.com:443/restproxy1
Taleo-
https://nmdemo113.taleo.net/smartorg/iam/accessmanagement/login.jsf?lang=en&redirectionURI=https://nmdemo113.taleo.net/smartorg/smartorg/common/toc.jsf
Access End Date | 22-FEB-2019
Login Username | Robert.Jackman or Conrad.Hagan
Login Password | 6rM5wF1c Copy to clipboard
HCM-
https://ucf1-zaqy-fa-ext.oracledemos.com/main.html
Password- 6uwKvkXK7

## Questions
Questions
Mobile back end is using which back end?